ToR- Evaluation of the Strategy of Innovation Activity (2016-2020) with the Action Plan

The Ministry of Economic Development invites national or international experts who fulfil the below listed criteria to apply for a short-term contract to carry out the final independent evaluation of the Strategy of Innovation Activity (2016-2020) with the Action Plan. The application/s should be submitted in Montenegrin language within the open Call for external expert. The title shall be marked “ToR – Final Evaluation of the Strategy of Innovation Activity (2016-2020) with the Action Plan.”

BACKGROUND INFORMATION

Montenegro has recognized the importance of innovation as one of the bases for its economic reconstruction and modernization. The country has in recent years undertaken a number of activities aimed at establishing a new institutional framework in support of innovation, as well as strengthening the existing potential for innovation through the implementation of various support programmes. This pointed to a need for developing regulatory and policy framework in the field of innovation activities. Montenegro is strongly focused on the improvement of innovation capacities within the country (regulatory environment, infrastructure and human resources), strengthening networking instruments and collaboration between all part-takers in the innovation system, and fostering innovation capacities of private sector.

In this context the focus of the Strategy of Innovation Activity (2016-2020) with the Action Plan (hereinafter: Strategy) has been directed at three main strategic goals: Increasing the capacities for innovation and technological development of Montenegro; Strengthening the instruments of integration and cooperation of actors in the innovation system; and Strengthening the potential for innovation in the business sector.

The evaluation should define the level of success of actions taken to address the key challenges identified in the Strategy:

  - Strengthening the institutional capacities, with a special focus on the new innovation infrastructure, which should become fully operational and sustainable;

  - Strengthening human resources for R&D through the continuous increase in the number of researchers and innovators, the organization of trainings necessary for the acquisition of skills in the field of research commercialization, as well as stimulating the selection of study programmes and research areas with potential to place the idea to the market, by PhD students;

  - Increasing investment in R&D, particularly by the business sector;

  - Strengthening the innovative potential of SMEs and their recognition in the system of innovation;

  - Support for cluster formation and strengthening their role in the innovation chain;

  - Raising awareness about the importance of protecting inventions by patent and increasing the number of patents that have found application in business;

  - Further strengthening ties of scientific-research (SR) institutions with the business sector;

  - Increasing participation in EU programmes that encourage innovation and technological development;

  - Directing SR work in the field of applied and development research on the real needs of enterprises; and

  - Providing adequate technology in SR institutions and enterprises, that is necessary for creating innovation.

DESCRIPTION OF THE ASSIGNMENT

The evaluator’s task is to analyse the relevance and overall performance of the implementation of the Strategy of Innovation Activity (2016-2020) with the Action Plan and undertake a comprehensive analysis to examine and review the outcomes and deliver comprehensive review report that will demonstrate an extensive understanding of the strengths and weaknesses of the implemented Strategy. According to this, the evaluator will analyse the relevance and overall performance of implementation of the Strategy.

Final evaluation report will show effectiveness of the results framework specifically the indicators, baselines and targets assessing how realistic/relevant they were and to what extent they have been reached. Additionally, the evaluation should provide an assessment on outcome and output indicators, their relevance, long term impact, sustainability of realised measures and effectiveness and efficiency in their delivery. It is expected that the evaluation results will be used to inform and improve programme management and that findings will be used in future decision-making processes and future strategic policy cycles.

The final evaluation will be an external, participatory and iterative process, which should be completed within a timeframe of 2 months, starting from 03 May 2021. The evaluation will also involve stakeholders participating in the process of creation and implementation of the Strategy of Innovation Activity (2016-2020) with the Action Plan, with particular focus on private sector input.

The main objectives of the evaluation are to:

1. identify, capture and disseminate lessons learned and achieved results over the implemented Strategy in order to explain and justify eventual deviations in Strategy performance (i.e. achievement of Strategy results) as a means of improving future strategic policies;

2. determine how effectively and efficiently the Strategy was implemented and the extent to which the net benefits have been achieved;

3. analyse the mechanisms responsible for producing change in Montenegrin innovation ecosystem.

Target groups to be included in the evaluation as survey respondents, interviewees, etc. are representatives of the project beneficiaries, relevant national and local authorities as well as policy makers and end users.

# Specific Tasks of the Evaluator

The main task of the Expert will be to prepare and deliver:

- to prepare and deliver the assessment and review of the annual reports as well as final report of the Strategy of Innovation Activity (2016-2020) with the Action Plan implementation process;

- to review effectiveness of the results framework specifically the indicators, baselines and targets;

- to identify, capture and disseminate lessons learned over the implementation period in order to explain and justify deviations in Strategy performance (i.e. achievement of programme results) as a means of improving Strategy delivery;

- to determine how effectively and efficiently the Strategy is being implemented and the extent to which the net benefits have been achieved;

- to provide impact assessment of the Strategy;

- to analyse the mechanisms responsible for producing change and sustainable results after the finalization of the Strategy implementation;

- to analyse the new legal framework of innovation activity being adopted in 2020 and state the developments that have occurred in the strategy period which were not foreseen in the subject Strategy.

- to analyse whether another strategy “Smart Specialisation Strategy of Montenegro (2019-2024)” represents an upgrade of the subject strategy and if there is a need for a new Strategy of Innovation Activity or the Smart Specialisation Strategy represents an appropriate strategic framework for Montenegrin National Innovation System development.

The Project shall engage national or international senior consultant whose main task will be to prepare and deliver final evaluation report on the implementation of the Strategy of Innovation Activity (2016 - 2020) with the Action Plan.

The tasks of the evaluation services encompass:

- Assessment and review of the annual reports and other relevant documentation on the Strategy of Innovation activity implementation process, paying particular attention to the realization of Action plan activities against planned results and determined objectives and also the achievement of set-up indicators.

- Review effectiveness of the results framework specifically the indicators, baselines and targets assessing how realistic/relevant and measurable they are and make recommendations for improvement. Evaluation should provide detailed technical expertise on evaluation of outcome and output indicators. The evaluation shall take into account the following criteria:

- Relevance - responsiveness of implementation mechanisms to the achievement of three Strategic Goals and nine Priorities determined by the Strategy:

- To what extent are the objectives and priorities of the Strategy still relevant?

- To what extent is the Strategy relevant in relation to the real needs of private sector and Montenegrin economy?

- To what extent do the objectives defined in the Strategy correspond to the existing priority needs and capacities in Montenegro?

- To what extent were stakeholders involved in the implementation of the Strategy?

- To what extent is the Strategy related and harmonized with the process of European integration?

- Coherence - compatibility and consistency of the Strategy with other strategies, projects, public policies in the country, sector or institution:

- Is the Strategy building synergies and avoiding duplication with other strategies and documents / projects implemented by the Ministry? Is the complementarity with other actions sought/ensured?

- To what extent the innovation activity novelties introduced by the new legislation (2020) and Smart Specialisation Strategy (2019-2024) are coherent with the subject Strategy?

- Is there a compliance of the strategic document with the relevant international norms and standards that the Ministry adheres to?

- Is there complementarity, coherence and coordination with other actors and countries in the given policy area?

- Describe how the Strategy create added value while avoiding duplications.

- Effectiveness - the extent to which policy results are being achieved:

- Did the implementation of the Strategy and accompanying action plans proceed on the basis of the planned dynamics during the 5 years of duration?

- To what extent each of the activities / measures contributed to achieving the planned effect?

- To what extent have the goals been achieved or when could they be expected to be achieved? What is the progress of the Strategy in reaching specific objectives and expected results?

- Examine whether the decision-making processes at Strategy level are clear and transparent.

- What changes (positive and negative) have occurred?

- What were the factors that most influenced the achievement or non-achievement of the objectives (describe advantages that support implementation and disadvantages that hinder implementation)?

- In areas where effectiveness is low / high, which stakeholder steps have contributed the most to high effectiveness / insufficient progress (driving forces / limiting forces)?

- Did the structure and timing of calls for proposals support the delivery of the Strategy in the most effective way?

- Efficiency – the implementation mechanism as the most cost-effective way of delivering strategic policy measures:

- Is the strategy implemented in the most efficient way compared to the alternatives? To what extent are the costs commensurate with the benefits achieved?

- How adequate was the institutional and organizational structure for coordination, monitoring, reporting on implementation (did it encourage or hinder the implementation of the Strategy)?

- Impact assessment – the changes to which the Strategy has contributed and assess the contributions of the Strategy to achievements set in the result indicators:

- What happened as a result of the implementation of the Strategy? What is the real impact on the users?

- What has happened as a result of the implementation of the Strategy in terms of progress in meeting the criteria for EU accession?

- To what extent has the Strategy built SMEs' capacity to increase innovation?

- To what extent has the Strategy demonstrated innovation capacity building to deal with long-term innovation levels and support Smart Specialization Strategy?

- What would be the most likely consequences if the activities from the Strategy were stopped or abandoned?

- Have the Strategy results led to organisational change and learning, for example:  Improvements in organisational efficiency and effectiveness; Improvements in policy; Improvements in / increased political awareness or support?

- Have any changes in laws or regulations been implemented and has the Strategy contributed to placing topics higher on the political agenda?

- How has the Strategy demonstrated increased capacity of decisionmakers (in terms of new / adopted solutions; services; products and processes) to solving current challenges?

- Sustainability – the benefits continue after the completion of the strategic document:

- To what extent have the positive effects of the Strategy and action plans continued even after the cessation of funding?

- Is the implemented Strategy likely to produce a long-term and sustainable (financially, institutionally, etc.) impact on the target groups and/or policymakers?

- To what extent have stakeholder institutions designed and incorporated into their plans and systems necessary feedbacks and monitoring mechanisms that will ensure self-renewal (adjustment) to achieve the objectives?

- What is the degree of sustainability of the capacity of institutions identified as stakeholders in the Strategy and action plans?

- How sustainable are future actions in a given area of public policy in terms of funding?

- Based on above stated assessment and identified evaluation criteria, it is proposed that the evaluation deliverables consist of a comprehensive and thorough evaluation report in order to increase its visibility and readability. This should include the appropriate approach used, key findings, limitations or issues encountered, and a set of clear outputs and recommendations that can be used to inform on future management. It should be ensured that the standard of reporting meets the quality and effectiveness of the data to be gathered and supplied. It shall also identify recommendations for follow-up actions.

STRUCTURE OF THE EVALUATION REPORT

- The final evaluation report should reflect the following general structure:

- Summary of conclusions and recommendations

- Methodology – outlining the evaluator’ approach. The methodology should also include a statement of the evaluator’ assessments of strengths and weaknesses of the evaluation report.

- Analysis of the findings.

- Conclusions addressing the criteria questions asked in the Terms of Reference (ToR).

- Summary of the principle achievements and deficiencies of the Strategy.

- Recommendations for policy makers clearly graded in order of importance.

- Suggestions for improvements are also to be made on a long-term basis, including future aspects and various scenarios that might be useful for the following period.

- Key issues should be identified at the end of every section and the conclusions drawn should be based upon them.

- It is expected that evaluation report will be easy readable, illustrative, and well structured.

# Qualifications and expertise of the evaluator

The assignment shall be conducted by one evaluator who should satisfy the following criteria:

- University degree;

- Postgraduate education (MA/PhD) would be considered as an asset;

- Experience of at least 1 assignment with policy evaluation process in area relevant to the assignment and within the context of EU accession;

- A minimum of 2 years of working experience in designing, implementing or monitoring / evaluation of strategies / policies in the area of innovation, private sector development, smart specialisation or similar;

- Experience of at least 1 assignment in advising governments on policy development in the field of innovation, research, business sector development or similar;

- Proven ability to think strategically, express ideas clearly and concisely, work both independently and in a team, demonstrate respect for others;

- Experience of working in the Western Balkans would be a strong advantage;

- Excellent command of Montenegrin and English language, both spoken and written;

- Excellent computer literacy;

- Excellent communication skills.

Other competencies of the evaluator:

- Demonstrates integrity by modelling high human values and ethical standards;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Ability of critical and strategic thinking, knowledge of results-based management and reporting;

- Builds strong relationships with clients, focuses on impact and result for the client and responds positively to feedback;

- Consistently approaches work with energy and a positive, constructive attitude;

- Demonstrates good oral and written communication skills;

- Demonstrates ability to manage complexities and work under pressure, as well as conflict resolution skills.

# Reporting and deliverables:

The Evaluator shall submit the following deliverables in Montenegrin language:

- Draft Evaluation Report

- Final Evaluation Report

The Evaluator shall submit the deliverables to the following contact person:

Ivan Tomović, PhD, Senior Advisor in the Department for Innovation and Technology Development, Ministry of Economic Development, ivan.tomovic@mek.gov.me.

# Timeframe and location

The services of the Evaluator will be provided between May and July 2021. The estimated working days for the assignment are 20. The overall duration of the assessment may not exceed 60 calendar days from the commencement date. The tentative start date will be 03 May 2021. The implementation of the activities, including the submission of the final evaluation report should be completed at latest by end of July 2021. The Ministry shall provide comments to the Draft report within 7 calendar days upon receipt, and approval of the final evaluation report within 14 days. If necessary, the evaluator will re-submit the corrected Final Evaluation Report, following additional comments by the Ministry, within 14 calendar days from receipt of the comments.

The services under this contract shall be performed in Podgorica, Montenegro, although the expert will also have home-based days allocated for the execution of this contract. The target area to be covered by this project is the whole territory of Montenegro, and there may be a need for short term assignments outside of Podgorica.

# Specification of inputs

| - Tasks | - No. of days (up to) |
| --- | --- |
| - Assessment and review of the annual reports and other relevant documentation on the Strategy of Innovation activity implementation process, paying particular attention to the realization of Action plan activities against planned results and determined objectives and also the achievement of set-up indicators | - 3 |
| - Review effectiveness of the results framework specifically the indicators, baselines and targets assessing how realistic/relevant and measurable they are and make recommendations for improvement. | - 2 |
| - Conduction of interviews and surveys with target groups: representatives of the project beneficiaries, relevant national and local authorities as well as policy makers and end users. | - 5 |
| - Preparation and drafting of the Evaluation Report | - 7 |
| - Review of comments to the Draft Evaluation Report and preparation of the Final Report | - 2 |
| - Presentation of the Final Evaluation Report to the stakeholders and beneficiaries | - 1 |
| - Total – up to | - 20 |

# Contract Information

The nature of this contract is – fee-based contract. Agreed expert fee will be paid after the termination of the contract and approval of deliverables by the Ministry. The Ministry shall ensure that the expert is adequately supported and equipped with office equipment and in particular shall ensure that there is sufficient administrative provision to enable expert to concentrate on his/her assessment responsibilities. No office, secretarial, communication or transport facilities are due to be provided by the Beneficiary. The maximum contract value for this assignment is 4,999 € excl. VAT.

# Documents to be submitted to this call

- Application Cover letter with summary of CV in relation to the Call

- Full CV of the applicant

- Financial offer indicating gross daily expert fee and additional costs (travel, accommodation)

# Evaluation of the applications

Submitted applications will be evaluated by a three-member commission appointed by the Ministry of Economic Development. The commission will determine a number of criteria for evaluating candidates, whereby the evaluation will be based on 70% on qualifications and expertise, and 30% on the financial offer. Shortlisted applicants will be invited for an online interview with members of the Commission. The Commission will make a proposal for the selection of the best candidate, on the basis of which the Ministry will make a decision on the selection of an evaluator for the evaluation of the Strategy of Innovation Activity (2016-2020) with the Action Plan. The contract with the evaluator will be concluded by the Ministry.

# Mode and deadline for application submission

Completed and signed applications with supporting documents shall be submitted to the Ministry of Economic Development in one hard copy (original), at the following address: Rimski trg 46, 81000 Podgorica with the following remark: Application to the Call for external evaluator of the Strategy of Innovation Activity (2016-2020) with the Action plan. The applications also need to be submitted electronically to the following e-mail address: ivan.tomovic@mek.gov.me.

Deadline for application submission is 23 April 2021 at 14h.

Contact person in the Ministry of Economic Development:

Ivan Tomović, PhD

Senior Advisor in the Department for Innovation and Technology Development, Ministry of Economic Development

E-mail: ivan.tomovic@mek.gov.me